## Gantt Chart
PROJECT SCHEDULE | [6 empty] | Project Title: Face Detection |  |  | Team Members: Omar Fahmy, Mostafa Ahmed
| TASK DESCRIPTION | Start Date | End Date | Duration (Weeks) | Responsible Members | % Complete | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52
1 | Choose Project | 2025-10-27 | 2025-11-03 | 1 | Omar & Mostafa | 100% | bar: Project Title: Face Detection WK44
2 | Kickoff, tool setup, choose detector(s) | 2025-11-03 | 2025-11-17 | 2 | Omar & Mostafa | 70% | bar: Project Title: Face Detection WK45 to Project Title: Face Detection WK46
3 | Illumination and shadow study | 2025-11-10 | 2025-11-17 | 1 | Omar & Mostafa | bar: Project Title: Face Detection WK46
6 | Fairness check across skin tones and multiple faces | 2025-11-17 | 2025-11-24 | 1 | Omar & Mostafa | bar: Team Members: Omar Fahmy, Mostafa Ahmed WK47
4 | Occlusion study (mask, glasses, hand) | 2025-11-17 | 2025-12-08 | 3 | Omar & Mostafa | bar: Team Members: Omar Fahmy, Mostafa Ahmed WK47 to Team Members: Omar Fahmy, Mostafa Ahmed WK49
5 | Motion study, add simple tracking if needed | 2025-12-01 | 2025-12-15 | 2 | Omar & Mostafa | bar: Team Members: Omar Fahmy, Mostafa Ahmed WK49 to Team Members: Omar Fahmy, Mostafa Ahmed WK50
8 | Polish results, finalize slides and demo, rehearse | 2025-12-08 | 2025-12-15 | 1 | Omar & Mostafa | bar: Team Members: Omar Fahmy, Mostafa Ahmed WK50
7 | Start writing report draft, start with the presentation slides | 2025-12-08 | 2025-12-22 | 2 | Omar & Mostafa | bar: Team Members: Omar Fahmy, Mostafa Ahmed WK50 to Team Members: Omar Fahmy, Mostafa Ahmed WK51
Formulas:
End Date = [Start Date]+[Duration (Weeks)]*7
Start Date = [Start Date, row above]+7